## Sheet1
Update: 25.02.13 14:47	No	Description	Fate Status	Doc Status	Author	File	Guide	est. Time	Remark
FATE	311709	FCoE: Add new FC Sysfs from upstream	Validation	Rejected	ccraft	stor_admin.xml	Storage Guide		Nothing to document, because fcoe_sysfs was added to the kernel, but the control interface did not make it into SP3.
FATE	312231	[BETA1] YaST support for LIO target (iSCSI, FCoE)	Implementation	Done	ccraft	stor_admin.xml	Storage Guide		FcoE part will not be implemented in SP3 GM, so only iSCSI part was documented
FATE	312888	btrfs quota support for subvolumes	Validation		ccraft	stor_admin.xml	Storage Guide
FATE	313521	Define disk order for MD Raid with YaST (YaST Partitioner)	Done		ccraft	stor_admin.xml	Storage Guide
FATE	313624	Include support for MD RAID in user space (mdadm/mdmon) to support Grantley platform	Validation		ccraft	stor_admin.xml	Storage Guide
FATE	313626	Update Enclosure LED Utilities to latest	Validation		ccraft	stor_admin.xml	Storage Guide
FATE	313905	Add support for lvm thin provisioning to yast2-storage	Done		ccraft	stor_admin.xml	Storage Guide
FATE	314134	MPIO Multipath.conf defaults and parameter config enhance	Validation		ccraft	stor_admin.xml	Storage Guide
FATE	314163	multipath support for SCSI persistent reservations	Validation		ccraft	stor_admin.xml	Storage Guide
FATE	314580	[DOCU] Document storage limitations	Evaluation	Done	ccraft		Storage Guide
FATE	309433	Include 3rd Party Apache Module (mod_security2) in SLES	Done	Done	fs	apache2.xml	Administration Guide	1
FATE	312751	[AFTER 11-SP3 FCS] snapper: cleanup rules based on free space and/or fill-level	Ready	Postponed	fs	snapper.xml	Administration Guide	0.5	Late delivery (planned for 09/10 2013)
FATE	313010	snapper: role based snapshot / rollback management	Done	Done	fs	snapper.xml	Administration Guide	0.5
FATE	313041	snapper / YaST2 snapper: create / modify snapshots	Done	Done	fs	snapper.xml	Administration Guide	0.5
FATE	313165	Add support for apache2-mod_auth_kerb	Done	Done	fs	apache2.xml	Administration Guide	0.5
FATE	313518	[DOCU] Document a trigger in /etc/sysconfig/yast2 to enable disable snapshots on YaST startup	Implementation	Done	fs	snapper.xml	Administration Guide	0.5
FATE	313860	support for LVM thin provisioned snapshots in snapper	Done	Done	fs	snapper.xml	Administration Guide	0.5
Bugzilla	732769	Explain and enforce why to use UTC in CMOS/BIOS		Done	fs	inst_yast2.xml	Administration Guide	1
FATE	313136	/etc/pki/nssdb support in Firefox	Implementation	Done	fs	apps_firefox.xml	Applications Guide	0.5
Bugzilla	802387	Update kexec part in the SLED autoyast documentation		Done	fs	ay_bigfile.xml	AutoYaST	?
FATE	313422	[DOCU] Extend AUTOYAST Documentation for qeth and lcs devices	Implementation		fs	ay_bigfile.xml	AutoYaST	0.5	mvidner is already working on it
Bugzilla	805270	AutoYaST documentation contains screenshot from SLES8		Done	fs	ay_bigfile.xml	AutoYaST	0.5
FATE	308838	Add script/button/option to erase all Registration Data	Done	Done	fs	inst_yast2.xml	Deployment Guide	0.5
FATE	312134	[DOCU] PXE for SLES for System z (zPXE)	Ready	Done	fs		Deployment Guide	2	Input from mpost pending
FATE	312662	Installation via USB	Done	Done	fs	inst_yast2.xml	Deployment Guide	1	Input needed.
FATE	312875	Add PLDP info to SLE install, YaST tools	Done	Done	fs	inst_yast2.xml	Deployment Guide	1
FATE	313527	[META] Secure Boot for UEFI 2.3.1	Ready	Done	fs	inst_yast2.xml	Deployment Guide	2	Stuff that affects installation
FATE	313922	Add scripts to s390x installation media initrd to configure network and installation server(s)	Implementation	Postponed	fs		Deployment Guide	1	Postponed, is still (Beta 3) work in progress
FATE	314318	Register URL to add-on product on install command line	Done	Done	fs	deployment_remote.xml	Deployment Guide	0.5
Doc Comment	16433	UEFI boot / installation		Done	fs	inst_yast2.xml	Deployment Guide	1	http://doccomments.provo.novell.com/comments/16433
FATE	314489	[UEFI] Secure boot support in installer DVD	Done	Done	fs		Deployment Guide	1
FATE	314490	[UEFI] secure boot support during installation	Done	Done	fs		Deployment Guide	1
Bugzilla	760809	Deployment Guide for SLES11 SP2 doesn't list either the z196 or z114 zEnterprise systems as being tested and supported		Done	fs		Deployment Guide	0.5
Bugzilla	615838	ASCII terminal installation methode in instsys not documented		Rejected	fs		Deployment Guide	3	Bug closed with NORESPONSE
Bugzilla	803987	Installer proposes deletion of prep partition		Done	fs	ppc*.xml	Deployment Guide	0.5
FATE	314368	Supported Virtualization Hosts	Implementation	Done	fs	x86_prep_nsysreqs.xml	Deployment Guide	0.5
FATE	310914	[BETA1] Technology preview: KVM support on s390	Implementation		fs		Virtualization with KVM	7	Check with ihno
FATE	314101	Support for paravirtualized I/O on s390 - kernel part	Validation		fs		Virtualization with KVM	1	KVM Guide for zSeries
FATE	313599	Virtual Machine Lock Manager for kvm/qemu/libvirt	Validation	Done	fs		Virtualization with KVM	2
FATE	313979	libvirt DAC Isolation (kvm)	Validation	Done	fs		Virtualization with KVM	2
FATE	313981	libvirt support for QEMU network helper for unprivileged users (kvm)	Validation	Done	fs		Virtualization with KVM	3
FATE	313994	virt-manager improvements to allow configuring of PCI passthrough devices at VM creation (kvm and Xen)	Done	Done	fs		Virtualization with KVM	2
FATE	314369	Supported Virtualizated Guests	Implementation	Done	fs		Virtualization with KVM	0.5
FATE	314371	Supported Virtualization Limits (KVM)	Implementation	Done	fs		Virtualization with KVM	0.5
Doc Comment	18969	Installing Para-Virtualized Drivers on Windows			fs		Virtualization with KVM	0.5
FATE	311403	Hotpluging of Bonding Slaves - userland (not YaST)	Done	Done	jfriedl	net_*.xml	Administration Guide	0.5
FATE	312521	ZYpp transaction auditing	Done	Done	jfriedl	zypper.xml	Administration Guide	0.5
FATE	312733	Command line interface to set hostname	Done	Done	jfriedl	net_*.html	Administration Guide	0.5
FATE	313278	Support filters in the "Online Update" YaST dialog	Done	Done	jfriedl	yast2_you.xml	Administration Guide	0.5
FATE	313445	zypper src download	Done	Done	jfriedl	zypper.xml	Administration Guide	0.5
FATE	305051	Repository enabled PTF delivery	Implementation	Rejected	jfriedl	yast2_sw.xml	Deployment Guide	0.5	Looks like no documentation is needed
FATE	313985	New package: libnetfilter_queue: Support 'failopen' when using netfilter's NFQUEUE target	Done	Done	jfriedl		System Analysis and Tuning Guide	1
Bugzilla	800807	Description of how to trigger text/graphical installer is inacurate		Done	jfriedl	x86_prep_boot.xml	Deployment Guide	0.5
FATE	313527	[META] Secure Boot for UEFI 2.3.1	Ready	Done	ke		Administration Guide	7	General UEFI documentation
FATE	314528	[DOCU] update documentation for Secure Boot	Implementation	Done	ke		Administration Guide	5
FATE	314578	[DOCU] Document current limitations in a UEFI Secure Boot Context	Ready	Done	ke		Administration Guide	1
FATE	312459	add cgroup support in tc / iproute2	Validation	Done	ke	tuning_cgroups.xml	System Analysis and Tuning Guide	1
FATE	314173	[DOCU] Update tuning guide and publish on SUSE web page add compiler and tools sectio	Ready	Rejected	ke		System Analysis and Tuning Guide	5	FATE rejected by mmatz
Bugzilla	754946	Missing YaST2 LDAP Dokumentation		Done	ke	security_ldap.xml	Security Guide	2
Bugzilla	764297	Old Syntax in /sles11/singlehtml/book_security/book_security.html#cha.security.ldap		Done	ke	security_ldap.xml	Security Guide	0.5
FATE	313848	Include flash-player-properties	Done	Done	taroth		Applications Guide	1
FATE	313905	Add support for lvm thin provisioning to yast2-storage	Done	Done	tbazant	lvm.xml	Deployment Guide	1
FATE	313309	support for "ipset"	Validation	Rejected	tbazant	security_firewall.xml	Security Guide	2	neither supported by YaST nor /etc/sysconfig - therefore something that should be mentioned in the Release Notes rather than in the Admin Guid
FATE	313454	kdump with vlans	Validation	Done	tbazant	tuning_kexec.xml	System Analysis and Tuning Guide	1
FATE	313875	[DOCU] Improve Tuning Guide with results from the Field	Implementation	Done	tbazant		System Analysis and Tuning Guide	5	Work with Lars Pinne's slides attached to the feature.
Doc Comment	21241	Fix rddtools diagram		Done	tbazant	utilities.xml	System Analysis and Tuning Guide	0.5	http://doccomments.provo.novell.com/comments/21241
FATE	313526	[DOCU] Improve PCI passthrough documentation for libvirt+kvm	Ready	Done	tbazant		Virtualization with KVM	3
FATE	313969	QEMU network helper for unprivileged users (kvm)	Validation	Done	tbazant		Virtualization with KVM	2
FATE	314368	Supported Virtualization Hosts	Implementation	Done	tbazant		Virtualization with KVM	0.5
FATE	314369	Supported Virtualizated Guests	Implementation	Done	tbazant		Virtualization with KVM	0.5
FATE	314370	Supported Virtualization Limits (XEN)	Implementation	Done	tbazant		Virtualization with KVM	0.5
FATE	314754	Include virtio-blk-data-plane (qemu)	Evaluation	Done	tbazant		Virtualization with KVM	2
FATE	314781	QEMU master feature	Evaluation	Done	tbazant		Virtualization with KVM	2
FATE	312709	Pygrub needs to know which entry to select	Done	Rejected	tbazant	xen_*.html	Virtualization with XEN	1	no need to document
FATE	313223	[DOCU] Lack of documentation about xenstore capabilities	Ready	Done	tbazant	xen_*.xml	Virtualization with XEN	2
FATE	314491	[UEFI] Secure boot support in Xen	Done	Rejected	tbazant		Virtualization with XEN	1	no need to document
Doc Comment	19835	Fix dead http link		Done	tbazant	xen_ha_setup.xml	Virtualization with XEN	0.5	http://doccomments.provo.novell.com/comments/19835
Doc Comment	20105	Fix dead http link		Done	tbazant	xen_virtualization_vhost.xml	Virtualization with XEN	0.5	http://doccomments.provo.novell.com/comments/20105
Doc Comment	21642	Fix links to OES product pages		Done	tbazant	xen_*.xml	Virtualization with XEN	0.5	http://doccomments.provo.novell.com/comments/21642
Bugzilla	801957	Classify parameters of yast partitioner are not present in documentation		Done	tbazant	yast2_manpart.xml	Deployment Guide	1
Bugzilla	806753	X server is not configured when installing over ssh, documentation should mention that		Done	toms	deployment_remote.xml	Deployment Guide	0.5
Bugzilla	803514	Reference in documentation regarding installation from smb points to README which does not contain any details		Done	toms	deployment_remote.xml	Deployment Guide	0.5	Waiting for bnc#804432
FATE	310250	Enhance NFS for scalability via pNFS (client)	Validation	Done	toms	net_nfs.xml	Administration Guide	2	Status for SP2: Done
Bugzilla	801051	Backports (Apache version in SP3)	Done	Done	toms	sle_update.xml	Deployment Guide	1
Doc Comment	18786	Explain backup recovery in case the update failed	Done	Done	toms	sle_update.xml	Deployment Guide	1	http://doccomments.provo.novell.com/comments/18786
FATE	313283	[DOCU] Support and document the BOOTIF option in linuxrc	Ready	Done	toms	deployment_remote.xml	Deployment Guide	0.5	Problem: linuxrc is documented on the wiki
Bugzilla	791390	Missing information in documentation about specific install details over SSH		Done	toms	deployment_remote.xml	Deployment Guide	0.5
FATE	313068	[BETA1] GSSAPIKeyExchange in openssh	Ready	Done	toms	security_ssh.xml (security_kerberos.xml)	Security Guide	0.5
FATE	313910	Add tipcutils userspace RPM package	Done	Rejected	toms		System Analysis and Tuning Guide	2	Problem: TIPC “alone” is just as useful as another library. Applications need to support the TIPC protocol in order to be useful.
FATE	314132	[ECO] Wagon upgrade - Add support for custom script execution	Done	Done	toms	sle_update.xml	Deployment Guide	1
FATE	312769	support for user mapping with NFSv4 + Kerberos	Validation	Postponed		hardening.xml	Security and Hardening Guide		To be done by draht? Status: submitted for SP3
		Sum						103.5

Fate entries that are unclear
FATE	304512	[DOCU] Patch terminology standard	Ready		ALL		ALL	3	Needs terminology which does not exist, yet, see comment #19.
FATE	311770	vPro: AMT support - kernel driver, AMT Configuration Utility, Local Manageability Service	Validation	Rejected	NEW		Administration Guide	4	Moved to Release Notes
FATE	312302	[DOCU] Improve documentation about storage and partitioning best practices	Evaluation		NEW		System Analysis and Tuning Guide	5	This can quickly become HUGE. The specific stuff mentioned in DocImpact looks like it should be documented via TIDs to me. PENDING, needs more information.
FATE	314174	[DOCU] Whitepaper to highlight the SDK compiler benefits (GCC 4.7)	Ready		NEW		WHITEPAPER	4	Unlear who is going to write this paper.
FATE	314520	[DOCU] Document Xen → KVM migration	Ready		NEW		WHITEPAPER	5	Our role in this is unclear. Same goes for deadlines.
FATE	312159	Technology preview: Provide libguestfs	Done		NEW		WHITEPAPER		Not for the manuals. Still unclear who will document and where the documentation should go.
FATE	312924	[DOCU] Document, how to effectively use KMPs -- was: update zypper functionality to effectively use	Implementation		NEW			2	Work with Scott Bahling
FATE	313491	[DOCU] Document MD RAID Use Cases and recover strategies - was: MD raid should recover automatically when failing disk is back again	Evaluation		NEW				Storage Guide or HA?